## RICs
Cause	Effect	Impact	Response	Custodian	Dates	Occurrence
Hosting issues	• Unable to demo product to client	Very High	Prepare: / • Choose a reliable hosting service		03/02/2022	14/02/22 - Issues relating to the hosting of the Splunk Environment using Amazon Web Services (AWS). AWS required payment to be provided for the environment to be hosted and this being a student-lead project no budget was available for this.
Team members intentionally not completing tasks	• Project completion is delayed / • Friction between team members	High	Mitigate: / • Regular team meetings / • Commit to support each other	Sergio - PM	03/02/2022	25/02/22 - Issues with one team member not contributing, before being addressed by PM the team member messaged and explained their confusion with the project scope but was up to date with the information and began to contribute.
Time contingencies due to unforseen circumstances	• Tasks may not be completed on time / • Resources taken away from other tasks	High	Mitigate: / • Clear communications between team members / • Sharing responsibilities	Sergio - PM	03/02/2022
Poor communication between team members	• Tasks may not be completed to desired specification / • Ideas and opinions may be missed	High	Mitigate: / • Agree working routines and communications / • Decide on a shared loction for the documentation / • Set up a project task board	Sergio - PM	03/02/2022	25/02/22 - After communication with team member struggling with the project scope, weekly meetings were restructured so all team members were aware of the weekly tasks
Conflict of ideas between team members	• Project could be delayed until team members come to an agreement / • Team members may become unmotivated	Medium	• Openly discuss all ideas during team meetings / • Allow members to vote on conflicting ideas / • Build trust	Sergio - PM	03/02/2022	14/03/22 - Website Layout and structure ideas between team members were conflicting and preventing the team moving forward. Team meeting was held where all the team members voted on their preferred layout, in turn meaning the entire team chose the final website design.
Project specification is difficult to implement	• Product does not work as intended / • Project cannot be completed within the specified timeframe	Medium	• Adjust product specification for the team skill level / • Sufficient product testing / • Cross-evaluate	Sergio - PM	03/02/2022	21/02/22 - Issues with the initial project scope, was too difficult to implement using Splunk software, collectively agreeed to abandon the idea of hosting our whole environment on Splunk and switched to creating a front end website and using the Splunk software to search through the database.
Final product does not match initial specification	• Product not suitable for intended purpose / • Client unsatisfied with final product	Medium	• Review and follow client specification document		03/02/2022
Software issues	• Completed tasks may no longer work / • Stalls progression of other tasks	Medium	• Update software if required / • Troubleshoot software issues		03/02/2022
Final product is not user friendly	• The client may be unable to use the product as intended / • Affects user engagement	Low	• Create detailed tutorial as a guide for new users / • Informative introduction page		03/02/2022
Complexity of questions	• Product not suitable for intended purpose / • Users may be unable to progress through questions	Low	• Consider the intended users / • Ensure questions are informative		03/02/2022	04/04/22 - Team members believed some of the questions were too repetitive and easy. The plan was set out to create more questions and provide the user with more diverse questions.